## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: yapvm
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2024-03-04 |  |  |  |  | March | [27 empty] | April
Scrolling increment: | 0 | time axis 2024-03-04 to 2024-04-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-03-04 to 2024-04-28
2024-04-01
Basic objects representation | High Risk | V, S, U | 0% | 2024-03-04 | 10
Basic interfaces | Med Risk | V, S | 0% | 2024-03-12 | 7
Internal data structures | Low Risk | U, S | 0% | 2024-03-14 | 14
Parser | Low Risk | V | 0% | 2024-03-04 | 3
2024-04-29
Interpreter | High Risk | V, S | 0% | 2024-03-25 | 21
Scope | Low Risk | S, U | 0% | 2024-03-30 | 14
Basic GC implementation | Med Risk | U, S | 0% | 2024-04-07 | 18
Threads | High Risk | V | 0% | 2024-04-04 | 25
2024-05-27
Optimized GC | Med Risk | V, S | 0% | 2024-05-01 | 14
Optimized interpreter | Low Risk | U, S | 0% | 2024-05-14 | 10
Threads optimized | High Risk | V | 0% | 2024-05-05 | 12